## HOW TO USE
CJEX 26 — OPERATION JOINT VENTURE
J4 Phase 2 Factor Analysis — Sustainment & Logistics ¦ Cell Chief Resources (CCR) ¦ 04 May 2026 ¦ [Security Classification]
HOW TO USE THIS WORKBOOK
Sheet 2 — FACTOR ANALYSIS | Factor statement, Deduction, Conclusion, Risk Rating, MRO Impact (1/2/3), Critical Operational Requirements (COR) reference, and owning J-branch
Sheet 3 — MRO COMPARISON | Side-by-side logistics verdict for each MRO against the 4-constraint hierarchy: Class III Fuel → APOD/SPOD throughput → MSR security → HNS reliability. Uses CAN/CANNOT/SHOULD/SHOULD NOT/MUST language
Sheet 4 — CORs REGISTER | Critical Operational Requirements (COR) derived from the factor analysis. Ranked, with precondition / SACEUR referral flags and J4 action column.
Sheet 5 — RISK SUMMARY | Consolidated risk register. Each risk cross-referenced to factor, domain, and COR. Risk rating uses NATO 5x5 likelihood × consequence matrix compressed to HIGH / MEDIUM / LOW for speed.
COLOUR KEY:RISK RATINGS
HIGH (RED) | Factor presents a pass/fail constraint or an existential risk to sustainment continuity. Requires COMJFC / SACEUR action.
MEDIUM (AMBER) | Factor presents a significant risk that degrades operational reach or tempo if unmitigated. Requires J4 mitigation action.
LOW / MANAGEABLE (GREEN) | Factor is a known limitation that can be planned around. Monitor and re-evaluate.
CRITICAL: Constraint vs Limitation | CONSTRAINT = cannot be changed by the commander (terrain, SPOD berth count, 7-day handling unit preparation, GoSL collapse, national caveats). LIMITATION = reduces capability but can be mitigated (HNS conditionality, fuel availability, MSR security).
Sources | Refs: [A] Serial 5 MRO 1 May 2026 ¦ [B] Serial 3 Scenario ¦ [C] Serial 8 Logistic Considerations ¦ [D] Serial 7 COMJFC Guidance ¦ [E] Serial 12 Forces Available ¦ [F] AJP-4(C V1) ¦ [G] JDP 4-00 4th Ed ¦ [H] COPD V3.1 Oct 2023

## FACTOR ANALYSIS
CJEX 26 — J4 PHASE 2 FACTOR ANALYSIS — SUSTAINMENT & LOGISTICS ¦ Cell Chief Resources (CCR) ¦ 04 May 2026 ¦ [Security Classification]
Analytical basis: COPD V3.1 Phase 2 ¦ AJP-4(C V1) Allied Joint Logistics Doctrine ¦ JDP 4-00 ¦ Serial 5 (MROs) ¦ Serial 8 (Logistics) ¦ Serial 3 (Scenario) ¦ Serial 7 (COMJFC Guidance)
DOMAIN | ID | FACTOR (Significant factual statement with operational implication) | DEDUCTION (So what is the significance?) | CONCLUSION (So what can/should/must be done?) | RISK RATING | MRO 1 IMPACT | MRO 2 IMPACT | MRO 3 IMPACT | COR REF | J-BRANCH | REFS
INITIAL ANALYSIS
| HI-01 | Serial 8 states that initial movement must include 30 DOS (per doctrine , with 7 days forward and 23 in reserve); Class III is POL, one Class III DOS for a brigade is approximately 70 tonnes, and fuel demand is adjusted by operation type, terrain and climate factors. Serial 8, Logistic Considerations, Supplies / Classes of Supply / Calculation factors for Sierra Leone operation; CJEX26_J4_Study_Pack.pdf pp.25–26. | Fuel consumption becomes a direct arithmetic constraint: every additional brigade or aviation-heavy force package creates daily tonnage that must enter through limited SPOD/APOD capacity before combat power can be generated. Fuel therefore constrains all MROs before other commodities become decisive. | Class III / fuel should be treated as the first-order sustainment constraint. WAFOR must sequence Class III as a priority commodity and confirm a fuel role-specialisation / lead nation before committing to MRO 2 or MRO 3.
| HI-02 | Serial 8 states that NATO forces require 30 CDOS endurance: 7 CDOS in the combat zone and 23 CDOS available; JTF forces must be stand-alone for up to 30 days. Serial 8, Logistic Considerations, Supplies; CJEX26_J4_Study_Pack.pdf p.25. | The operation cannot be judged only by initial entry. It must build and maintain a 30-day fuel/sustainment base. This makes pre-positioning and throughput a prerequisite for declaring IOC/FOC rather than a later sustainment activity. | Fuel stock build-up must precede operational tempo. WAFOR should not declare force elements operationally viable beyond limited tasks until minimum forward Class III stocks are established.
| HI-03 | Serial 8 states force generation succeeded only for handling units for two SPOD and one APOD; handling units need 7 days in theatre to prepare APOD/SPOD and staging areas before receiving troops. Serial 8, Logistic Considerations, Movement / Reception and staging standards; CJEX26_J4_Study_Pack.pdf p.24. | The number and readiness of entry points limits how fast combat power can arrive. A single late handling unit delays every subsequent aircraft/ship regardless of force readiness or strategic lift availability. | APOD/SPOD throughput is the second-order constraint after fuel. JLSG/handling units must be first-lift and arrive D-7; entry-point preparation is a pass/fail condition for all MROs.
| HI-04 | Serial 8 states only two SPODs are available: FREETOWN and CONAKRY; both have limited NATO berths, only enough staging/parking to organise one brigade at a time, and a brigade must spend three days in staging before onward movement. Serial 8, Logistic Considerations, Movement / Reception and staging standards; CJEX26_J4_Study_Pack.pdf p.24. | SPOD discharge is not the only limit: staging capacity forces sequential brigade flow. MRO 1 can be manageable; MRO 2 and MRO 3 create backlog unless CONAKRY is available and sequencing is tightly controlled. | FREETOWN cannot be the sole SPOD for MRO 2/3. WAFOR must use CONAKRY for larger MROs and treat staging capacity as a hard ceiling on force flow.
| HI-05 | Serial 3A states QE II Quay at FREETOWN has six berths and over 30,000 m² container parking, but remaining free capacity is assessed as near zero due to massive humanitarian assistance use. Serial 3A, Initial Joint Intelligence Estimate, Freetown/QE II Quay port data; CJEX26_IRL Reading Pack 1 White, p.3A-11. | The nominal port capacity overstates real military availability. Humanitarian use competes directly with military throughput, making FREETOWN a bottleneck even before enemy action or labour limits are considered. | WAFOR should not plan FREETOWN as a clean military port. A CIMIC/J4 deconfliction mechanism and dedicated military/humanitarian windows are required before deployment starts.
| HI-06 | Serial 8 gives road movement rates of up to 300 km/day for supply columns, 100 km/day for larger units, and states a Convoy Support Centre is required for every day of transport; it also notes there is no functioning common-carrier railway. Serial 8, Logistic Considerations, Movement by road / rail; CJEX26_J4_Study_Pack.pdf p.24. | Even if supplies enter theatre, they only become useful if they can move forward. With no rail alternative, MSRs are the distribution system; every contested or degraded road day reduces forward sustainment and extends the deployment window. | MSR security is the third-order constraint: after fuel and entry points, WAFOR must secure primary MSRs and establish CSCs before forward force deployment beyond the FREETOWN/Lungi lodgement.
| HI-07 | Serial 7 directs staff to assess how climate/weather and the lack of GLOCs and infrastructure will affect WAFOR mission; Serial 3/Study Pack notes rainy season onset in May, terrain constraints and MSR interdiction by AFRC/RUF. Serial 7, COMJFC Initial Planning Guidance, key issues (climate/weather; lack of LLOCs and infrastructure); CJEX26_J4_Study_Pack.pdf p.23. Serial 3 scenario summary; CJEX26_J4_Study_Pack.pdf p.26. | The scenario itself makes movement reliability a commander's issue, not a branch detail. Rain and poor infrastructure convert secondary/feeder routes into non-viable assumptions and increase dependence on a small set of primary roads. | WAFOR should base sustainment on primary MSRs only, treat off-road/feeder access as air-resupply or pre-positioning problems, and table route security as a combat task required before logistics movement.
| HI-08 | Serial 7 states the Government of SIERRA LEONE faces internal RUF and external LIBERIAn threats and that the crisis combines humanitarian, political and economic instability; legal considerations state SOFA exists and further HNS/transit agreements may be concluded with GUINEA, GAMBIA etc. Serial 7, Commander’s Initial Planning Guidance, review of situation; CJEX26_IRL Reading Pack 2 Yellow, pp.7-1 to 7-2. Serial 4A legal considerations; CJEX26_IRL Reading Pack 1 White, Legal Considerations/UNSCR section. | HNS exists legally but not necessarily functionally. SIERRA LEONE's government and commercial base may not deliver reliable port labour, fuel, transport, contracting or infrastructure support at the point of execution. | HNS reliability should be treated as the fourth constraint: vital but less immediate than fuel/entry/MSR because it can be mitigated by organic logistics, CSO, MSAs and alternative basing—if planned early.
| HI-09 | Serial 7 requires coordination and liaison with Government of SIERRA LEONE, GUINEA, LIBERIA, Nigeria, UN actors, ECOMOG, IOs/NGOs and humanitarian actors; Serial 8 says supplies can be reduced by HNS, CSO, CUI and logistics coordination. Serial 7, Coordination and Liaison Requirements; CJEX26_J4_Study_Pack.pdf p.23. Serial 8, Supply requirements; CJEX26_J4_Study_Pack.pdf p.26. | External support is not automatic; it must be negotiated, coordinated and deconflicted. Without coordination, HNS/CSO/IO resources become competing demands that consume the same ports, labour, fuel, roads and warehouses. | WAFOR must establish J4/CIMIC coordination and early contracting authority, but HNS remains a reliability risk beneath the higher-order physical constraints of fuel, throughput and MSR security.
APOD / SPOD
APOD / SPOD | EP-01 | LUNGI INTERNATIONAL AIRPORT is the sole APOD. Under active MANPAD (SA-14 Gremlin) attack. Intermittently closed. APOD handling unit requires 7 days in-theatre preparation before receiving troops. GAMBIA offers an intermittent forward operating base. | Single APOD with active threat = single point of failure for all time-sensitive air delivery (medical resupply, munitions, personnel reinforcement). 7-day lead time means handling unit MUST be in first lift or all subsequent air inflow is delayed by exactly that amount. | WAFOR CANNOT treat LUNGI as a reliable sole APOD. WAFOR MUST activate GAMBIA as contingency APOD and MUST deploy handling unit at D-7. APOD air defence (Counter-MANPAD) is a pre-condition for reliable air sustainment. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-2 | J4/J3 | [C][D]
APOD / SPOD | EP-02 | SPOD FREETOWN (SLFNA): 4 berths, 2 available to NATO. Max draft 9.7/11.2m. Working day 12 hours only. 150m berth = 1 RoRo = 6 hours offload. Staging area capacity: ONE brigade simultaneously. 3-day minimum staging before onward movement. | At 2 berths / 12hr day: approx 4 RoRo/day throughput max. MRO 1 (9 RoRo) = min 3 days SPOD ops. MRO 2 (18 RoRo) = 5-6 days. MRO 3 (42+ RoRo) = 11-15 days. ONE brigade in staging at a time means sequential force flow only — cannot parallel-load two brigades. | WAFOR SHOULD treat FREETOWN SPOD as the primary entry point for MRO 1 only. For MRO 2-3, FREETOWN alone is INSUFFICIENT. Staging constraint is a hard ceiling on force flow rate regardless of SPOD throughput. | HIGH | MANAGEABLE | HIGH IMPACT | CRITICAL | COR-1 | J4/J1 | [C][E]
APOD / SPOD | EP-03 | SPOD CONAKRY (GNCKY), GUINEA: 4 berths (2 available to NATO). Berths 113-270m. Max draft 10.5/13m. Technical Agreement NOT YET SIGNED. No lethal force on GUINEAn soil. GUINEA's critical economic asset — CONAKRY harbour protection is a key GUINEAn national interest. | CONAKRY is essential for MRO 2 and 3 — without it both options face a logistics culmination point before achieving MSOs. The unsigned TA is a strategic-level precondition, not a J4 matter. However, J4 must flag: until TA is signed, CONAKRY cannot appear in any MRO 2/3 logistics plan as a confirmed asset. | WAFOR CANNOT plan MRO 2 or 3 without CONAKRY. SACEUR MUST secure GUINEA TA before deployment orders issued. J4 SHOULD propose a maritime harbour protection quid pro quo through J5 to accelerate agreement. CONAKRY force protection model must not rely on armed WAFOR ashore — GUINEA constraint is absolute. | HIGH | LOW IMPACT | CRITICAL | CRITICAL | COR-1 | J4/J5 | [C][F]
APOD / SPOD | EP-04 | GAMBIA air and naval facilities: available as possible intermittent forward operating base per Serial 8. Not yet formalised. Could serve as contingency APOD and additional maritime logistics node. | For MRO 3, GAMBIA provides critical third-entry-point redundancy and reduces dependency on LUNGI/FREETOWN single corridor. Without GAMBIA, MRO 3 deployment cannot be completed within an operationally relevant timeframe. | WAFOR SHOULD formalise GAMBIA basing arrangement during ACTPRED for MRO 3. For MRO 1-2, treat GAMBIA as contingency, activated if LUNGI closes. Technical Agreement for GAMBIA must be a planning action, not an execution contingency. | MEDIUM | LOW IMPACT | LOW IMPACT | HIGH IMPACT | COR-1 | J4/J5 | [C]
APOD / SPOD | EP-05 | Purple Gate and Coupling Bridge: The point at which national deployment responsibility transitions to NATO/JLSG control is the SPOD staging area (FREETOWN/CONAKRY). Until this is formally agreed between JLSG and all TCNs, port operations will default to national control — generating coordination failure. | Previous operations have lost 1-3 days of SPOD throughput to purple gate ambiguity on first ship arrival. In a single-SPOD scenario with 12-hour working days, 2 lost days = 8 RoRo ships not processed — equivalent to one full brigade delayed. | WAFOR MUST formally agree the purple gate and coupling bridge arrangements with all TCNs before first ship arrival. This is a JLSG command task in pre-execution, not an administrative nicety. JLSG must publish a Port Reception Authority document before D-Day. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-2 | J4 | [G]
APOD / SPOD | EP-06 | IO/NGO competition for SPOD/APOD: UNMSL, UNOCHA, UNJLC all require access to LUNGI APOD and FREETOWN SPOD. MRO 3 serial explicitly flags competition with IO/NGO for port access as a named risk. | In a 12-hour SPOD working day with 2 berths, every IO/NGO ship displaces a military RoRo. If not deconflicted, the humanitarian impulse will compete directly with force deployment tempo, extending the high-vulnerability deployment window. | WAFOR MUST establish a CIMIC-led SPOD/APOD deconfliction mechanism before first forces arrive. J4 SHOULD propose dedicated windows for military vs humanitarian traffic. This is a planning requirement from Phase 2, not an execution problem. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-7 | J4/CIMIC | [A][G]
APOD / SPOD | EP-07 | LUNGI–FREETOWN estuary crossing / ferry dependency. LUNGI APOD is separated from FREETOWN logistics base by the estuary crossing. There is no bridge; movement depends on ferry, water taxi or craft capacity. | Even if LUNGI APOD remains open, APOD cargo, personnel flow, MEDEVAC and time-sensitive sustainment remain vulnerable if the crossing is congested, interdicted, sabotaged or weather-limited. Loss of the crossing isolates the APOD from the main theatre logistics base. | WAFOR MUST treat the LUNGI–FREETOWN crossing as a critical logistics node. J4/J3 Maritime must control crossing capacity, protect it, and plan rotary-wing or maritime contingency transfer for time-critical cargo. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-2 | J4 | [C]
CLASS III — FUEL
CLASS III — FUEL | F-01 | Class III base rate: 70 MT/bde/DOS. CDOS multiplier: PSO (1.0) × hilly terrain (1.2) × hot climate (0.9) = 1.08. Effective rate: 75.6 MT/bde/DOS. MRO 1 (1.5 bde equiv): 113 MT/DOS. MRO 2 (3 bde): 227 MT/DOS. MRO 3 (4 bde + armour + aviation uplift): ~418 MT/DOS. | MRO 3 daily fuel demand alone exceeds what FREETOWN SPOD can reliably deliver given competing cargo requirements. MRO 2 is at the upper limit of single-SPOD capacity. MRO 1 is manageable at FREETOWN but requires fuel to be sequenced as priority commodity. | Fuel is the primary sustainment constraint for all MROs. WAFOR MUST sequence Class III as the priority commodity in the deployment schedule for all MROs. For MRO 2-3, CONAKRY SPOD is not optional — it is arithmetic. A fuel role-specialisation nation MUST be confirmed in CJSOR. | HIGH | MANAGEABLE | HIGH IMPACT | CRITICAL | COR-4 | J4 | [C][F]
CLASS III — FUEL | F-02 | 30 CDOS required in theatre before operations (7 combat zone, 23 available). At MRO 1: 3,390 MT total Class III stockage required. MRO 2: 6,810 MT. MRO 3: 12,540 MT. No functioning national fuel distribution infrastructure in SIERRA LEONE. | Building CDOS to standard requires a sustained period of SPOD operations before the force is operationally capable. At MRO 3 scale, the stockage build-up itself generates a fuel import requirement that occupies most of SPOD throughput capacity during the first weeks. | WAFOR MUST plan a dedicated pre-positioning phase for Class III before combat forces declare IOC. WAFOR CANNOT declare IOC until minimum 7 CDOS combat zone stocks are established forward. Fuel pre-positioning is the first logistics task in theatre. | HIGH | MEDIUM IMPACT | HIGH IMPACT | CRITICAL | COR-4 | J4 | [C]
CLASS III — FUEL | F-03 | Aviation (Avn Bn: attack, transport, MEDEVAC) is fuel-intensive in hot, high-humidity tropical climate. Hot/high conditions reduce lift capacity and increase fuel burn by 15-20% versus temperate operations. Attack and MEDEVAC sorties cannot be curtailed for fuel economics. | Aviation fuel demand is non-discretionary in this JOA — MEDEVAC cannot be stood down to conserve fuel. Aviation fuel management must be planned as a separate fuel stream with dedicated forward fuelling points at LUNGI and potentially at forward operating bases. | WAFOR SHOULD plan aviation fuel as a separately tracked commodity with its own CDOS calculation. Dedicated aviation fuel tankers and forward fuelling points must be in the JLSG logistics base plan from D+7. This applies to all MROs with Avn Bn committed. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | HIGH IMPACT | COR-4 | J4/J3 Air | [C][E]
CLASS III — FUEL | F-04 | Role specialisation for fuel: no nation has yet been designated as fuel lead nation. Lead Nation concept for bulk fuel supply is doctrinely supported (AJP-4(A)) and operationally essential at MRO 2-3 scale in an austere theatre. | Without a confirmed fuel lead nation, Class III supply defaults to national procurement by each TCN — generating competing fuel contracts, different fuel grades, incompatible tank farms, and no single J4 authority for fuel prioritisation. This is the definition of artificial scarcity. | WAFOR MUST confirm a fuel role-specialisation nation in CJSOR before deployment. J4 SHOULD identify candidate nations with bulk fuel tanker capability and propose to COMJFC for CJSOR submission to SACEUR. | HIGH | LOW IMPACT | HIGH IMPACT | CRITICAL | COR-4 | J4 | [F]
CLASS III — FUEL | F-05 | Fuel storage and distribution capacity. Class III risk is not limited to total fuel tonnage. Bulk storage, fuel quality control, tanker availability, forward fuel points and distribution assets determine whether imported fuel can become usable operational reach. | A force may import sufficient fuel tonnage but still culminate if it cannot store, test, protect and distribute fuel to forward forces. MRO 2 and MRO 3 create a forward distribution problem that cannot be solved by SPOD throughput alone. | WAFOR MUST plan Class III as a complete system: import, storage, quality control, tanker distribution, forward fuel points and protection. A fuel role-specialisation nation must include storage and distribution capability, not only procurement. | HIGH | MEDIUM IMPACT | HIGH IMPACT | CRITICAL | COR-4 | J4 | [C][F]
MSR SECURITY
MSR SECURITY | MSR-01 | MSR FREETOWN–Bo (primary southern route): under active AFRC/RUF attack. UN convoys have been attacked. Essential for supply to Southern Province and forward elements at Bo. Distance approx 240km, mostly asphalted primary road. | Without this MSR, Southern Province cannot be supplied by land. Supply columns at 300km/day (secure) / 150km/day (contested) make the FREETOWN-Bo return trip 2 days secure or 3-4 days contested. Every extra day of transit is a day of reduced distribution to forward troops. | WAFOR CANNOT sustain forces in the Southern Province without FREETOWN-Bo MSR security. Route clearance and security is a combat task that MUST precede logistics convoy movements on this axis. J4 must plan dedicated Convoy Support Centres for this route from D+1. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-5 | J4/J3 | [B][C]
MSR SECURITY | MSR-02 | MSR FREETOWN–Kabala (northern route): under AFRC/RUF attack. Essential for supply to Northern Province (Makeni area). Distance approx 250km. Passes through partially contested terrain. | Northern Province supply depends entirely on this route once feeder roads become impassable in rainy season. AFRC/RUF interdiction of FREETOWN-Kabala simultaneously with FREETOWN-Bo would isolate both Northern and Southern Provinces from logistics support. | WAFOR SHOULD plan pre-positioned stocks at Makeni (minimum 14 DOS) before advancing forces to the Northern Province. Route security for FREETOWN-Kabala must be planned as a concurrent combat operation with logistics movement — not a sequential one. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-5 | J4/J3 | [B][C]
MSR SECURITY | MSR-03 | MSR Bo–Yonibana: under active AFRC/RUF attack. Secondary but important lateral route. Connects Southern Province to central area. Under attack now. | Interdiction of Bo-Yonibana removes the lateral LOC flexibility between southern and central supply areas. Forces the logistics system into a purely radial structure from FREETOWN — high vulnerability to single-point interdiction. | WAFOR SHOULD designate Bo-Yonibana as a secondary supply route, not a primary one, given current threat. Pre-position stocks at Bo to reduce dependency on this axis under operational tempo. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT | COR-5 | J4/J3 | [B][C]
MSR SECURITY | MSR-04 | Rainy season commences May 2026 — immediately. Feeder roads (4,277km total, 0% paved): inaccessible during rainy season. Secondary roads (2,091km, 46km paved): poor condition. Only 925km of primary roads paved. | The logistics footprint accessible by road reduces dramatically from May onwards. Any force element that cannot be reached by asphalted primary road is effectively cut off from routine resupply during rainy season. This includes most of the Eastern Province. | WAFOR CANNOT rely on secondary or feeder road access from May 2026. All logistics plans must be based on primary road access only. Forces deployed off primary roads MUST be air-resupplied or pre-positioned with 30+ DOS stocks before rainy season degrades routes. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-5 | J4/J3 | [B][C]
MSR SECURITY | MSR-05 | Convoy Support Centres: required for every day of transport movement. Brigade road movement rate: 100km/day. Supply columns: up to 300km/day (secure) / ~150km/day (contested). No functioning railway. 84km narrow-gauge private rail (Pepel-Marampa, iron ore only) — not available for military logistics. | A FREETOWN–Kenema supply run (250km) at contested rate requires 2 days each way = 4-day supply column cycle. At MRO 3 scale with multiple axes, the Convoy Support Centre requirement becomes a significant infrastructure task for the Engineer Battalion. | WAFOR MUST plan Convoy Support Centres on all primary supply axes before advance beyond FREETOWN. J4 SHOULD table a dedicated CSC construction programme in the J4 annex to the CONOPS. Engineer CSC construction must be sequenced before first supply column movement. | MEDIUM | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-5 | J4/J3 Engr | [C]
HOST NATION SUPPORT
HOST NATION SUPPORT | HNS-01 | Government of SIERRA LEONE (GoSL) assessed as on the verge of collapse. GoSL is the primary HNS provider within SIERRA LEONE — port workers, local contracts, infrastructure access, civil authority over logistics facilities. Near-collapse degrades all of these. | Any logistics plan that treats GoSL HNS as reliable has a false analytical foundation. Port workers at FREETOWN SPOD, warehouse staff, fuel distributors, local engineering contractors — all are dependent on a functioning civil authority that may not exist by the time forces arrive. | WAFOR MUST NOT plan GoSL HNS as a baseline assumption. Every logistics function currently assigned to GoSL must have a NATO organic or commercial alternative. ACTPRED and OLRT deployment MUST prioritise confirmation of actual GoSL HNS status within 72 hours of arrival. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-6 | J4/CIMIC | [B][D]
HOST NATION SUPPORT | HNS-02 | GUINEA HNS: willing in principle, subject to Technical Agreement. CONAKRY harbour. No lethal force on GUINEAn territory. Technical Agreements required for APOD, SPOD, and additional airbases. TA not yet signed. | GUINEA HNS is real capability (CONAKRY SPOD is better than FREETOWN in draft and berth length) but contingent on political conditions being maintained. GUINEA's primary motivation is economic — CONAKRY harbour protection. WAFOR can leverage this but only through J5 diplomatic channels, not J4 unilateral action. | WAFOR MUST pursue GUINEA TA as an immediate ACTPRED priority through J5. J4 SHOULD propose maritime harbour protection quid pro quo. GUINEA HNS at CONAKRY SHOULD be planned as a firm logistics asset for MRO 2-3 — but only once TA is signed. Until then: planning assumption requiring confirmation. | HIGH | LOW IMPACT | CRITICAL | CRITICAL | COR-1 | J4/J5 | [C][D]
HOST NATION SUPPORT | HNS-03 | Mutual Support Agreements (MSAs): AJP-4(A) provides for bi- and multi-lateral MSAs between TCNs. Especially useful for small contingents co-located with larger forces. MSAs reduce redundant NSE deployment and achieve logistics economies of scale. | At MRO 3 scale with 15,000-20,000 personnel from multiple nations, the total NSE footprint without MSAs will be enormous — competing for the same port real estate, warehousing, and logistics resources. MSAs are the mechanism to prevent this. | WAFOR SHOULD initiate MSA development between Tier 2 and 3 TCNs during ACTPRED. J4 SHOULD propose MSA templates for medical, fuel, and Class I to COMJFC for tabling at the force generation conference. NSE co-location in the FREETOWN logistics base area is a MUST from the outset. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4 | [F]
HOST NATION SUPPORT | HNS-04 | NSE positioning: AJP-4(A) para 2.22 recommends TCN NSEs co-locate in theatre main support areas, close to CJTF HQ, with LOs at appropriate levels in command structure. No NSE positioning directive has been issued. | Dispersed NSEs competing for port capacity and warehousing will generate artificial scarcity and increase coordination costs. CJFLCC exercises coordinating authority over NSEs in AOO — this must be actively used, not held in reserve. | WAFOR MUST issue NSE positioning guidance as part of the JLSG SOI/logistics directive. NSE LOs MUST be embedded with JLSG from arrival. Failure to enforce NSE co-location from D+0 will create port congestion that compounds the staging area constraint. | MEDIUM | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [F]
HOST NATION SUPPORT | HNS-05 | Commercial contracting and external sustainment: contracted fuel, water, food, port handling, and engineering will supplement organic NATO logistics capacity. Commercial sector in SIERRA LEONE is degraded by conflict and GoSL near-collapse. Contracting authority and enabling budget required in pre-execution. | Commercial contracts cannot be established once operations commence in a contested environment. Contracting must begin during ACTPRED. An enabling budget is identified in Serial 7 as a named requirement. Without pre-contracted services, external sustainment defaults to organic military capacity — which is insufficient at any MRO scale. | WAFOR MUST establish contracting authority and an enabling budget in pre-execution. J4 SHOULD identify priority commercial contracts (fuel, water, food, port handling) and submit to COMJFC for funding authority. Serial 7 explicitly requires this [Ref D]. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-6 | J4 | [D][F]
RSOMI / DEPLOYMENT
RSOMI / DEPLOYMENT | RS-01 | JLSG, LBU (Logistics Base Unit), and RSOI Unit must arrive and be operational before main force flow begins. 7-day handling unit preparation requirement at both APOD and SPOD. JLSG is the operational logistics command that enables all subsequent force deployment. | If JLSG arrives with the main force, the logistics base is being built while forces are simultaneously trying to use it. This is the most common cause of RSOMI failure in coalition operations. The 7-day rule is not guidance — it is a planning constraint derived from the handling unit preparation requirement. | WAFOR MUST sequence JLSG, LBU, RSOI Unit, and handling units as the FIRST elements in the deployment order. This is a doctrinal requirement per AJP-4(A) para 2.13. ACTPRED package must include JLSG HQ and handling units at D-7 minimum. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-2 | J4 | [C][F]
RSOMI / DEPLOYMENT | RS-02 | The 4Ds (Distance, Destination, Demand, Duration): RSOMI process from SPOD/APOD to operational deployment area. Staging area constraint (one brigade simultaneously) forces sequential force flow. Each brigade must complete 3-day staging before onward movement before next brigade can enter staging. | For MRO 2 (3 brigades), sequential staging = minimum 9 days of staging operations before all brigades reach their deployment areas — on top of SPOD throughput time. This is the critical path for force deployment, not the sailing time. | WAFOR SHOULD plan the deployment sequence with staging area rotation as the binding constraint, not SPOD throughput. The second and third brigades must have holding areas identified near the SPOD before the first brigade clears staging. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-2 | J4/J3 | [C][G]
RSOMI / DEPLOYMENT | RS-03 | Air Assault Brigade entry option: 5 days to move into theatre by C-17/Airbus/organic assets with basic load (Cl I, III, V). No sea transport required for initial entry. Provides a faster initial lodgement capability bypassing SPOD constraint for the opening phase. | An air assault initial entry (Lt Inf BG via LUNGI if APOD is open) compresses the D-Day to IOC timeline significantly for MRO 1. However, air assault forces require sea-delivered logistics build-up within 5-7 days — so the SPOD sequence must follow immediately. | WAFOR SHOULD consider air assault initial entry (Lt Inf BG) as the lodgement force for MRO 1, with SPOD delivering logistics build-up and heavier forces in parallel. This is contingent on LUNGI being open — which requires Counter-MANPAD operations as a precondition. | MEDIUM | HIGH IMPACT | MEDIUM IMPACT | LOW IMPACT |  | J4/J3 | [C][E]
RSOMI / DEPLOYMENT | RS-04 | JLSG location: FREETOWN logistics base area (port proximity). Staging area for RSOMI: FREETOWN SPOD staging zone (one bde capacity). JLSG forward elements: LUNGI APOD for air logistics management. Component logistics HQs: co-located with component HQs per command arrangements. | JLSG location in FREETOWN creates a LUNGI-FREETOWN water crossing dependency for all APOD-delivered cargo. The LUNGI-FREETOWN ferry is the only crossing — no bridge. This is a choke point within the JLSG's own logistics base management that must be planned for explicitly. | WAFOR MUST plan LUNGI-FREETOWN ferry capacity and control as a J4 task from D-Day. JLSG forward element at LUNGI MUST have organic transport to the ferry. Loss of ferry = loss of APOD-sourced cargo delivery to the main logistics base. Contingency: rotary-wing transfer of time-critical items. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [C]
RSOMI / DEPLOYMENT | RS-05 | Strategic RoRo sealift: MRO 1 = ~9 ships; MRO 2 = ~18 ships; MRO 3 = 42+ ships (full division) or 84+ (corps). LIBERIA has assessed submarine capability and 10+ combat aircraft capable of interdiction. Merchant vessels carrying military equipment are high-value targets. Naval escort mandatory. | A LIBERIAn strike on RoRo vessels during force flow would be catastrophic — loss of a brigade's vehicles and equipment at sea, with no rapid replacement mechanism. The deployment phase is the period of maximum vulnerability: force is fragmented, logistics base is incomplete, combat power is below threshold. | WAFOR MUST task naval escort for all strategic RoRo lift from D-Day. This is not a supporting effort — it is a precondition for the deployment to function. The SSK and SNMG must be tasked for RoRo escort as a primary mission, not residual capacity. WAFOR CANNOT accept deployment phase risk without this. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-3 | J4/J3 Maritime | [B][C]
SUPPLY CLASSES
SUPPLY CLASSES | SC-01 | Class I: 4 kg food/person/day. Water: 85 litres/person/day (operation-specific planning average). At MRO 1 (5,000 personnel): 20 MT food/day, 425,000 litres water/day. MRO 3 (20,000 personnel): 80 MT food/day, 1.7M litres water/day. Local food procurement highly uncertain given GoSL near-collapse. | Water at 85L/person/day in a tropical climate is not a luxury — it is a medical requirement. At MRO 3 scale, daily water demand is 1.7 million litres. No functioning national water distribution system. Water production must be organic (Reverse Osmosis Water Purification Units) or contracted. | WAFOR MUST include organic water production in the JLSG logistics base plan. Class I (water) must be treated as a mission-critical commodity on par with Class III at MRO 2-3 scale. Local food procurement SHOULD NOT be relied upon — plan organic with contracted supplement. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4 | [C]
SUPPLY CLASSES | SC-02 | Class II: 10 MT/bde/DOS. Class V (ammunition): 166 MT/bde/DOS base rate. PSO consumption factor = 1.0. At MRO 3 (4 bdes): Class V demand = 664 MT/DOS. AFRC/RUF is lightly armed — conventional ammunition consumption likely lower than base rate initially. LIBERIAn conventional threat would drive Class V demand sharply upward. | Class V planning at PSO rate (1.0) is appropriate while AFRC/RUF is the primary threat. If LIBERIA intervenes directly (MRO 3 scenario), Class V demand could spike to high-intensity rates (factor 3.0-5.0) with no warning time. Pre-positioned Class V stocks must account for the LIBERIAn escalation scenario. | WAFOR SHOULD plan Class V at PSO rate (1.0) for initial CDOS, with a reserve of 15 CDOS at high-intensity rate held at the logistics base for immediate forward release if LIBERIA intervenes. Ammunition convoy security is a dedicated task — munitions cannot travel on shared supply columns without escort. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4 | [C][F]
SUPPLY CLASSES | SC-03 | Medical — Role 1/2/3: 3x Role 1, 1x R2 Enhanced MTF in ARF Tier 1. MRO 2 adds Med Support Group. MRO 3 requires Role 3 MTF. Austere/challenging environment noted in all three MROs in Serial 5. MEDEVAC (Avn Bn) is non-discretionary. ALP-16 munitions risk assessment required for explosive ordnance handling. | Role 3 MTF is in ARF Tier 2 (10-30 days NTM) — meaning it arrives after the initial lodgement. The period before Role 3 arrives is the highest medical risk window: forces are conducting operations with only R2E capability. MEDEVAC to Role 3 requires a functioning LUNGI APOD or maritime MEDEVAC. | WAFOR MUST plan a medical lead nation for the Role 3 MTF. WAFOR SHOULD identify an intermediate MEDEVAC routing (maritime or GAMBIA) for the period before Role 3 is in-theatre. Cross-cutting medical requirements (CRSV, child soldiers encounter protocols, infectious disease) must be in the Role 1/2 SOPs from D-Day. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4/J2 Med | [A][C]
SUPPLY CLASSES | SC-04 | CDOS standard: 30 DOS total (7 combat zone, 23 available in theatre). Reaction forces: 10-day minimum endurance. Forward elements off primary roads: J4 recommends 14 DOS minimum given resupply uncertainty in rainy season. | Building 30 CDOS from zero in an austere theatre with a constrained SPOD and contested MSRs is a logistics challenge in itself. The CDOS build-up phase (D+0 to IOC) is a period when the force is at its most vulnerable logistically — combat power is building but stocks are not yet at standard. | WAFOR MUST plan the CDOS build-up as a phased logistics operation in its own right. J4 should present COMJFC with a CDOS build-up timeline for each MRO — showing when the force reaches 7 CDOS (combat zone minimum) and when it reaches 30 CDOS (full standard). These dates define the IOC and FOC milestones. | MEDIUM | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [C]
COMPETING DEMANDS
COMPETING DEMANDS | CD-01 | Active humanitarian crisis: IDPs displacing, food insecurity, medical system collapse in contested areas. UNMSL humanitarian convoys on MSRs simultaneously with WAFOR military convoys. UNJLC coordinating humanitarian logistics. Competition for fuel, water, port capacity, warehousing, transport vehicles, and skilled labour. | In a country where commercial resources are already depleted by conflict and near-governmental collapse, WAFOR arrival generates immediate competition for every logistics commodity. WAFOR's organic fuel demands will crowd out civilian fuel supply to hospitals and water pumping stations. This is not a humanitarian planning problem — it is a WAFOR logistics sustainability problem. | WAFOR MUST establish a civil-military logistics coordination cell (CIMIC/J4 interface) from D+0. WAFOR SHOULD establish protected fuel and water aGLOCations for critical civilian infrastructure as part of the logistics planning — this prevents WAFOR from inadvertently becoming the cause of the humanitarian crisis it is deployed to mitigate. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-7 | J4/CIMIC | [D][F]
COMPETING DEMANDS | CD-02 | IO/NGO logistics impact: UNMSL, UNOCHA, UNJLC, ECOMOG all present. IO/NGO can support WAFOR through provision of sustainment functions; compete for limited resources; and make requests for WAFOR sustainment function support (convoy protection, MEDEVAC). | WAFOR logistics capacity will be requested by IO/NGO from day one. Every MEDEVAC sortie in support of an NGO is a sortie not available for WAFOR casualties. Every fuel aGLOCation to UNMSL is fuel not in WAFOR forward stocks. These are real trades, not hypothetical ones. | WAFOR MUST establish clear policies for IO/NGO requests for sustainment support before D-Day — including approval authority, reimbursement where applicable, and capacity limits. J4 SHOULD coordinate with CIMIC to produce a J4/IO-NGO coordination SOP for issue with the logistics directive. | MEDIUM | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-7 | J4/CIMIC | [D][F]
COMPETING DEMANDS | CD-03 | IDP and refugee movement: Serial 7 [Ref D] flags IDP/refugee impact as a specific COMJFC attention area. Mass population movement will use the same primary road network as WAFOR logistics. FREETOWN area already under population pressure. IDP camps may be sited near logistics base areas. | Mass IDP movement on MSRs will degrade supply column movement rates and create unpredictable route blockages. IDP camp proximity to logistics base creates force protection complexity and potential for diversion of supplies. Planning for IDP movement is not a CIMIC-only task — it is a logistics route management task. | WAFOR SHOULD deconflict IDP movement corridors with MSR supply routes in the joint effects coordination process. J4 MUST plan for degraded MSR movement rates (50% reduction) during peak IDP movement periods. This affects CDOS build-up timelines. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4/CIMIC/J2 | [D]
COMPETING DEMANDS | CD-04 | Artificial scarcity: multiple nations operating in the same region competing for essential resources (fuel, water, food, communications, contracted services). This is explicitly identified in AJP-4(A) as a key risk in coalition operations. No JLSG resource coordination framework yet established. | Without active coordination, TCNs will independently contract for the same commodities from the same suppliers — driving up prices, reducing availability, and creating resentment between coalition partners. This has occurred in every major coalition operation since Kosovo. | WAFOR MUST establish a JLSG-led resource coordination framework from D-Day. JLSG should act as the single point of coordination for all commodity contracting, preventing bilateral nation-to-supplier relationships that generate artificial scarcity. This requires OPCOM authority from COMJFC over theatre logistics. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4 | [F]
GOVERNANCE / CROSS-CUTTING
GOVERNANCE / CROSS-CUTTING | GC-01 | UNSCR 2198 (3 April 2026): Chapter VII mandate. Authorises all necessary means. 24-month duration ceiling. Legal basis for HNS agreements, ROE, and use of force to protect logistics elements. SOFA/Technical Agreements with GoSL and GUINEA required before forces can operate on their territory. | The legal framework is in place at the strategic level. At the operational logistics level, what matters is whether Technical Agreements have been translated into practical HNS arrangements. SOFA coverage of logistics elements on MSRs must be confirmed — particularly in GUINEA where the 'no lethal force' condition must be reconciled with force protection requirements. | WAFOR MUST confirm that SOFA/TA coverage extends explicitly to logistics elements operating in GUINEA and on GoSL territory. The 'no lethal force on GUINEAn soil' constraint must be reflected in JLSG force protection SOPs for CONAKRY. J4 must raise this with J5 before CONAKRY SPOD is activated. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4/J5/J9 | [C][D]
GOVERNANCE / CROSS-CUTTING | GC-02 | Cross-cutting topics: protection of civilians, children and armed conflict, women peace and security, CRSV, cultural property protection, combating trafficking, sexual exploitation and abuse, building integrity. All must be reflected in logistics planning and commercial contracts per COPD/NATO policy. | These are not administrative add-ons. AFRC/RUF use of child soldiers means logistics convoy force protection rules of engagement must address encounters with child combatants. CRSV documentation in this JOA means Role 1/2 medical SOPs must include clinical pathways. Contractor oversight must include anti-trafficking provisions. | WAFOR MUST embed cross-cutting topic requirements in: logistics SOPs (convoy protection); medical SOPs (CRSV, child soldier encounters); and all commercial contracts (anti-trafficking, building integrity). J4 SHOULD request J9/LEGAD sign-off on logistics contract templates before execution. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | MEDIUM IMPACT |  | J4/J9/LEGAD | [H]
GOVERNANCE / CROSS-CUTTING | GC-03 | Munitions and explosives risk: AJP-4(A) para 2.26. Munitions owned by nations, not NATO. ALP-16 risk assessment required. MANPAD threat to LUNGI means aircraft carrying ammunition are priority targets. MSR interdiction of ammunition convoys is an existing AFRC/RUF tactic. Storage site selection critical. | An AFRC/RUF strike on an ammunition convoy or storage point would be strategically significant. The Class V storage site must be separate from the main logistics base and located with consideration of proximity to populated areas and adjacent MSR security. | WAFOR MUST conduct ALP-16 munitions risk assessment before establishing Class V storage. Storage sites must be separated from logistics base by minimum safe distance. Ammunition convoys MUST have dedicated escort — cannot share columns with other supply classes. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4/J3/LEGAD | [F]
GOVERNANCE / CROSS-CUTTING | GC-04 | Collective sustainment: AJP-4(A) establishes the principle of collective responsibility. Nations bear ultimate responsibility for their own forces but collective sustainment arrangements (role specialisation, mutual support, lead nation) are the doctrinal mechanism for operational efficiency in coalition operations. | In a 15-20 nation coalition at MRO 3 scale, purely national sustainment is operationally inefficient and logistically chaotic. The JLSG must be empowered by COMJFC to coordinate and, where necessary, direct logistics resources — otherwise the logistics system defaults to the lowest common denominator of parallel national efforts. | COMJFC MUST grant JLSG coordinating authority over theatre logistics from D-Day. JLSG MUST develop a collective sustainment framework (role specialisation proposals, MSA templates, NSE positioning directive) for COMJFC approval at the earliest planning conference. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [F]
GOVERNANCE / CROSS-CUTTING | GC-05 | Pre-execution budget and enabling funds: Serial 7 [Ref D] explicitly identifies an enabling budget as a requirement for contracting preparation, OLRT, engineering setup, and initial information activities. Common-funded cost estimated at EUR 300-450M over 24 months. Early contracting requires upfront authority. | Logistics contracting cannot begin without budget authority. Pre-execution contracting (fuel, water, port handling, engineering) requires funding before the OPLAN is approved — this is the enabling budget requirement. Without it, J4 is unable to establish the external sustainment baseline that all MROs depend on. | WAFOR MUST request enabling budget authority from NAC/SACEUR as an immediate CRM. J4 SHOULD submit a pre-execution contracting plan to COMJFC with a prioritised list of contracts and estimated costs for enabling budget request. This must happen before ACTPRED, not after. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT | COR-6 | J4 | [D]
GOVERNANCE / CROSS-CUTTING | GC-06 | LIBERIAn threat to logistics: LIBERIA provides AFRC/RUF with MANPADs (SA-14), sanctuaries, arms, intelligence, and training. Receiving Russian ISR (EO, SAR, SIGINT). Developing offensive cyber capability targeting LUNGI Airport systems. 10+ combat aircraft capable of interdiction. Possible submarine capability. | The adversary understands that LUNGI and FREETOWN SPOD are single points of failure. LIBERIAn ISR capability means the logistics base location and deployment sequencing are being observed in near-real-time. The logistics build-up phase is the period of maximum vulnerability — LIBERIA may choose to strike during this window. | WAFOR MUST assume LIBERIA has persistent ISR on LUNGI APOD, FREETOWN SPOD, and the LUNGI-FREETOWN crossing. Logistics base hardening, dispersal of stocks, and deception regarding deployment sequence must be planned from D-Day. Cyber protection of LUNGI Airport logistics systems (fuel management, cargo tracking) is a J6/J4 shared task. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4/J2/J6 | [B]
GOVERNANCE / CROSS-CUTTING | GC-07 | Reinforcement and sustainment network activation: the JLSN must be activated and nodes linked before operational tempo increases. This includes formalising node locations (FREETOWN logistics base, LUNGI APOD, CONAKRY, GAMBIA), establishing LOC security arrangements, and linking to strategic-level movement control. | The JLSN is not self-activating. It requires deliberate J4 action to establish each node, link them through movement control, and integrate national and NATO logistics flows. In previous operations, failure to formally activate the JLSN has resulted in logistics nodes operating in isolation — unable to redirect cargo or resources between nodes. | WAFOR MUST formally activate the JLSN as a J4 command task in pre-execution. A JLSN architecture diagram should be produced and approved by COMJFC before D-Day. All logistics nodes (FREETOWN, LUNGI, CONAKRY, GAMBIA) must have designated node commanders with clear lines of authority to JLSG. | HIGH | HIGH IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [C][F]
ADDITIONAL FACTORS
ADDITIONAL FACTORS | MED-01 | Strategic MEDEVAC / Role 3 gap before full medical system arrives. Role 3 medical capability arrives with ARF Tier 2 (10-30 days NTM), while LUNGI APOD is under MANPAD threat and may close intermittently during the critical initial lodgement phase. | Initial lodgement forces may conduct operations with only Role 1 / Role 2 Enhanced care available for 10-30 days. If LUNGI closes, strategic MEDEVAC and evacuation to Role 3 become fragile, increasing both operational and political risk. A serious casualty requiring Role 3 care with no viable MEDEVAC route is a strategic-level event. | WAFOR MUST identify an interim MEDEVAC pathway before D-Day, including maritime or GAMBIA routing if LUNGI is unavailable. Role 3 lead nation and patient evacuation policy must be confirmed before MRO 2 or MRO 3 forward operations begin. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4/JMED/J3 Air | [A][C][E]
ADDITIONAL FACTORS | ENG-01 | Engineer infrastructure capacity and priority conflict. Engineer tasks include route repair, bridge assessment, base construction, water production support, force protection works, SPOD/APOD improvement and Convoy Support Centre construction — all simultaneously demanded from a single Engineer Battalion. | Engineer demand will exceed available capacity, especially under MRO 2 and MRO 3. Without prioritisation, engineer assets will be pulled between mobility, sustainment and force protection tasks, delaying MSR opening and logistics base establishment. Every day of delay in CSC construction extends the contested convoy window. | WAFOR MUST publish an engineer priority of work linked to logistics sequencing. Route repair, bridge classification, CSC construction and SPOD/APOD sustainment works must be prioritised before forward deployment beyond FREETOWN. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-5 | J4/J3 Engr | [C]
ADDITIONAL FACTORS | MOV-01 | Movement control / deconfliction capacity. Military, national, HNS, contractor, UN, IO/NGO and humanitarian movements will compete across the same APODs, SPODs, staging areas, MSRs and convoy routes simultaneously from D-Day. | Even where physical capacity exists, poor movement control will create artificial congestion, port delay, duplicated convoy movements and loss of tempo. MRO 2 and MRO 3 require active movement prioritisation, not passive coordination. Without theatre-level movement authority, each nation will optimise for its own force — not the joint force. | WAFOR MUST establish a theatre movement control mechanism under JLSG/J4 before first force arrival. Movement priorities, convoy windows, port call-forward procedures and humanitarian deconfliction must be agreed and published before D-Day. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT | COR-7 | J4/J3/CIMIC | [C][D][F]
ADDITIONAL FACTORS | C2-LOG-01 | Authority of JLSG over national logistics / NSEs. National Support Elements and TCN logistics chains will operate in theatre while JLSG is expected to coordinate scarce logistics resources. JLSG's authority over NSEs is coordinating, not command. | If JLSG lacks authority to prioritise scarce port capacity, storage, fuel, convoy slots and common services, the logistics system defaults to national competition. This creates artificial scarcity, duplicated effort, and undermines the force-level sustainment plan. AJP-4(A) is clear that JLSG requires COMJFC backing to make this work. | COMJFC MUST grant JLSG clear coordinating authority over theatre logistics from D-Day. NSE positioning, liaison, reporting and common-user logistics priorities must be issued before deployment begins. JLSG cannot perform its function without this authority being explicit. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4 | [F]
ADDITIONAL FACTORS | FP-LOG-01 | Protection of logistics nodes. FREETOWN SPOD, LUNGI APOD, CONAKRY SPOD, fuel farms, staging areas, ammunition sites, JLSG HQ and Convoy Support Centres are all high-value targets. The adversary does not need to defeat manoeuvre forces to break the operation. | Strikes, sabotage or indirect attacks against logistics nodes could halt force flow, destroy stocks or delay deployment during the period of maximum vulnerability. LIBERIA has the ISR to identify these nodes and the capability to attack them. AFRC/RUF has demonstrated willingness to attack logistics infrastructure on MSRs. | WAFOR MUST make logistics node protection a named force protection task. J3/J4 must identify critical logistics nodes, assign protection forces, harden and disperse stocks, and integrate air defence, counter-sabotage and access control from D-Day. | HIGH | HIGH IMPACT | HIGH IMPACT | CRITICAL | COR-2 / COR-3 | J4/J3 FP/J2 | [B][C]
ADDITIONAL FACTORS | INFO/CYBER-01 | Cyber attack on port, airport and logistics information systems. Logistics throughput depends on port scheduling, airfield systems, cargo tracking, fuel management, communications and movement control information systems. LIBERIA is actively developing offensive cyber capability and has targeted LUNGI Airport systems. | A cyber or information systems failure could collapse throughput without a kinetic attack. If WAFOR loses visibility of cargo, fuel stocks or convoy priorities, scarce entry-point and MSR capacity will be misallocated. Manual fallback for a modern logistics operation is degraded, slow and error-prone. | WAFOR MUST include logistics information systems in the J6 cyber protection plan. Cargo tracking, fuel management, port scheduling and movement control systems MUST have validated manual fallback procedures before D-Day. | HIGH | MEDIUM IMPACT | HIGH IMPACT | HIGH IMPACT |  | J4/J6/J2 | [B][C]
ADDITIONAL FACTORS | ENV-01 | Disease, heat, water sanitation and force health protection. SIERRA LEONE presents tropical disease (malaria, cholera, Lassa fever), high heat and humidity, poor sanitation and degraded civil health infrastructure. Water demand is 85 litres per person per day and local water systems are unreliable. | Disease and heat casualties may degrade force availability and logistics labour faster than enemy action. Poor sanitation or unsafe water at staging areas, logistics bases or forward locations could reduce operational endurance significantly and increase MEDEVAC demand at exactly the moment the medical system is least able to cope. | WAFOR MUST treat force health protection as a sustainment requirement. Organic water production (ROWPU), sanitation, vector control, heat injury prevention and medical surveillance must be included in the JLSG base plan from D-Day. | MEDIUM | MEDIUM IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4/JMED | [B][C]
ADDITIONAL FACTORS | TRANS-01 | Sustainment handover to UN / follow-on force. UNMSL and GoSL may be expected to inherit or support parts of the sustainment architecture after NATO establishes security conditions. MRO 3 may create a logistics system too large, complex or expensive for UNMSL or GoSL to absorb. | If transition is not planned early, WAFOR may become locked into a long-term sustainment burden that extends the NATO commitment well beyond the 24-month mandate ceiling. Building logistics infrastructure that only NATO can operate is a strategic liability. | WAFOR SHOULD design sustainment arrangements with transition in mind from Phase 2. J4 must identify which logistics functions can be handed over to UNMSL/GoSL, which require contractor support, and which must remain NATO responsibilities until conditions allow. | MEDIUM | LOW IMPACT | MEDIUM IMPACT | HIGH IMPACT |  | J4/J5/CIMIC | [A][D]

## MRO COMPARISON
CJEX 26 — MRO LOGISTICS COMPARISON ¦ J4 CCR ¦ 04 May 2026 ¦ [Security Classification]
Dutch language: CAN = logistically feasible ¦ CANNOT = logistically infeasible ¦ SHOULD = recommended action ¦ SHOULD NOT = strongly advised against ¦ MUST = precondition. Constraint hierarchy: Class III Fuel → APOD/SPOD Throughput → MSR Security → HNS Reliability.
CONSTRAINT / FACTOR | MRO 1 — LIMITED ENGAGEMENT | MRO 2 — MODERATE ENGAGEMENT | MRO 3 — DECISIVE ENGAGEMENT
CLASS III / FUEL | MANAGEABLE. WAFOR CAN sustain MRO 1 at 113 MT/DOS through FREETOWN SPOD provided fuel is sequenced as PRIORITY commodity. 30 CDOS = 3,390 MT — achievable within SPOD capacity. CONAKRY adds resilience but not required. | DEMANDING. WAFOR CAN sustain MRO 2 at 227 MT/DOS ONLY IF CONAKRY SPOD is operational. FREETOWN alone CANNOT deliver MRO 2 fuel demand. Fuel role-specialisation nation MUST be confirmed. WAFOR SHOULD NOT attempt MRO 2 without CONAKRY TA signed. | CRITICAL. WAFOR CANNOT sustain MRO 3 (~418 MT/DOS) through FREETOWN + CONAKRY alone. GAMBIA MUST be activated as third entry point. Fuel role-specialisation nation is non-negotiable. Class III is the single greatest risk to MRO 3 viability.
APOD / SPOD THROUGHPUT | MANAGEABLE. 9 RoRo ships, min 3 days SPOD ops at FREETOWN. Staging constraint (1 bde) is sufficient for MRO 1 force. Air assault initial entry viable if LUNGI open. JLSG MUST arrive D-7. Purple gate MUST be agreed before D-Day. | AT LIMIT. 18 RoRo = 5-6 days FREETOWN + staging rotation = 15-18 days total without CONAKRY. With CONAKRY: 8-10 days. WAFOR SHOULD NOT attempt MRO 2 without CONAKRY. LCC/Div HQ SHOULD flow via CONAKRY to decongest FREETOWN staging. | EXCEEDS CAPACITY. 42+ RoRo = 11-15 days SPOD ops with both SPODs. Staging rotation adds 18-27 days. Full deployment completion: 30+ days. LIBERIAn strike on RoRo in transit = catastrophic. Naval escort MUST be tasked. GAMBIA MUST be activated.
MSR SECURITY | MANAGEABLE given constrained geographic focus (FREETOWN + key areas). WAFOR SHOULD plan convoy escort from D+1. Feeder roads impassable from May — plan primary roads only. Pre-position 14 DOS at Bo as a MUST before any advance. | CRITICAL VULNERABILITY. MRO 2 extends to Eastern Province — 250-300km from FREETOWN through contested terrain. MSR security MUST precede force deployment on contested axes. Without secured MSRs, forces at Kenema will culminate while FREETOWN is over-supplied. | CORPS-LEVEL PROBLEM. All primary MSRs simultaneously in use. AFRC/RUF interdiction on any axis fractures supply. LIBERIAn cross-border threat on eastern MSRs. Dedicated route security battalion required. Convoy Support Centre network MUST be built before advance.
HNS RELIABILITY | TOLERABLE. Geographic focus limits HNS dependency to FREETOWN area. GoSL HNS uncertain but degradation manageable. GUINEA TA MUST be signed. Commercial alternatives MUST be contracted for all GoSL-dependent functions. | HIGH RISK in forward areas. GoSL HNS effectively absent in Bo and Kenema. Self-sufficient forward logistics elements MUST be planned for both areas from D-Day. All commercial contracts MUST be established in pre-execution. | SEVERE outside FREETOWN. WAFOR effectively running national logistics system in a failed state. Organic capability for ALL forward operations. NSE co-location and MSAs MUST be established. Role specialisation ESSENTIAL — without it MRO 3 logistics is unmanageable.
OVERALL J4 VERDICT | WAFOR CAN SUSTAIN MRO 1. Risk: MODERATE. Preconditions: GUINEA TA signed; JLSG deploys D-7; fuel as priority commodity; commercial contracts pre-established. | WAFOR CAN SUSTAIN MRO 2 IF CORRECTLY SEQUENCED. Risk: HIGH. Critical preconditions: CONAKRY TA signed; fuel role-specialisation nation confirmed; MSR security concurrent with forward deployment; CONAKRY SPOD fully operational. | WAFOR CAN SUSTAIN MRO 3 LONG-TERM — CANNOT SUSTAIN THE DEPLOYMENT PHASE without GAMBIA as third entry point. Risk: VERY HIGH during deployment. Preconditions: ALL CORs 1-7 met before D-Day. Deployment phase is the window of maximum vulnerability.

## CORs REGISTER
CJEX 26 — J4 CRITICAL OPERATIONAL REQUIREMENTS (SUSTAINMENT) ¦ COPD Phase 2 ¦ CCR ¦ 04 May 2026
CORs 1-3 are PASS/FAIL — no MRO 2 or 3 is executable without them. CORs 4-7 are serious operational risks that will materialise in execution if not addressed in pre-execution. All 7 must be in the Operational Advice Annex to SACEUR per COPD para 4.21.
COR ID | TITLE | COPD Assessment | DESCRIPTION | PASS/FAIL? | SACEUR REFERRAL? | J4 ACTION | ACTION BY | FACTOR IDs
COR-1 | GUINEA Technical Agreement for CONAKRY SPOD | Precondition for success | Signed TA must be in place before deployment orders are issued. Without it, CONAKRY SPOD cannot be planned as a confirmed asset. MRO 2 and 3 are not logistically executable without CONAKRY. | YES — MRO 2/3 | YES — SACEUR | Propose maritime harbour protection quid pro quo through J5. Confirm TA status at ACTPRED D-7. Flag to SACEUR if unsigned. | J4/J5 | EP-02, EP-03, HNS-02
COR-2 | JLSG and Sustainment Enablers Deploy D-7 | Mission essential force capability | JLSG HQ, LBU, RSOI Unit, APOD and SPOD handling units must arrive and be operational minimum 7 days before main force. This is a hard planning constraint from Serial 8. Purple gate must be agreed before D-Day. | YES — ALL MROs | YES — SACEUR | Draft ACTPRED package with JLSG as first lift element. Publish Port Reception Authority document before D-Day. Confirm 7-day slot in deployment order. | J4 | RS-01, RS-04, EP-01, EP-05
COR-3 | Naval Escort for Strategic RoRo Lift | Precondition for success | LIBERIA's submarine and air interdiction capability requires naval escort of all RoRo vessels from D-Day. Loss of RoRo in transit = loss of brigade equipment — irreplaceable within operational timelines. | YES — ALL MROs | YES — SACEUR | Confirm maritime escort task with J3 Maritime. Include as named task in CJSOR. Brief COMJFC on deployment phase vulnerability window. | J4/J3 Maritime | RS-05
COR-4 | Fuel Role-Specialisation Nation Confirmed in CJSOR | Mission essential force capability | Class III is the primary sustainment constraint. Without a dedicated fuel nation (bulk tankers, forward fuel points, JLSG integration), MRO 2-3 Class III demand cannot be managed organically. Must be named in CJSOR. | YES — MRO 2/3 | YES — SACEUR | Identify candidate nations at force generation conference. Submit role-specialisation proposal to COMJFC. Include fuel nation requirement in CJSOR submission. | J4 | F-01, F-02, F-04
COR-5 | MSR Security Operations Concurrent With Forward Deployment | Constraint | Combat forces MUST clear and hold primary MSRs before logistics columns can move. MSR security is not a logistics task — but the logistics chain depends on it entirely. Sequencing failure = forward force culmination. | NO — sequencing risk | NO — COMJFC | Table MSR security as a named enabling condition in the logistics annex. Ensure J3 sequencing places route clearance before supply column movement on all contested axes. | J4/J3 | MSR-01 to MSR-05
COR-6 | Contracting Authority and Enabling Budget in Pre-Execution | Critical in-theatre support and infrastructure | Commercial contracts (fuel, water, port handling, engineering) cannot be established in execution. Enabling budget required per Serial 7. Without pre-contracted external sustainment, organic military logistics capacity is insufficient for any MRO. | NO — planning risk | YES — budget authority | Submit pre-execution contracting plan to COMJFC. Identify priority contracts. Request enabling budget authority from NAC/SACEUR. Serial 7 explicitly supports this requirement. | J4 | HNS-05, GC-05
COR-7 | CIMIC/IO-NGO Logistics Deconfliction Mechanism | Reqirement | Competition for SPOD/APOD and logistics resources with UNMSL, UNOCHA, UNJLC must be managed by a formal deconfliction mechanism before D-Day. Improvising in execution generates artificial scarcity and delays force deployment. | NO — coordination risk | NO — COMJFC | Produce J4/CIMIC logistics coordination SOP. Establish dedicated traffic windows at SPOD/APOD for military vs humanitarian cargo. Brief CIMIC on IO/NGO sustainment request policy. | J4/CIMIC | EP-06, CD-01, CD-02

## RISK SUMMARY
CJEX 26 — J4 RISK SUMMARY ¦ Phase 2 ¦ [Security Classification] ¦ CCR ¦ 04 May 2026
Risk rating: HIGH = pass/fail constraint or existential sustainment risk ¦ MEDIUM = significant risk degrading reach/tempo ¦ LOW = known limitation, manageable with planning. Filter by Domain or MRO Impact.
FACTOR ID | DOMAIN | RISK TITLE | RISK STATEMENT | MITIGATION / J4 ACTION | MRO 1 | MRO 2 | MRO 3
EP-01 | APOD/SPOD | LUNGI APOD — Single Point of Failure Under Active MANPAD Threat | AFRC/RUF MANPAD attacks intermittently close LUNGI. 7-day handling unit preparation requirement. No alternative APOD confirmed in SIERRA LEONE. Entire air logistics line vulnerable. | Deploy Counter-MANPAD assets. Activate GAMBIA as contingency APOD. JLSG handling unit in first lift at D-7. | HIGH | HIGH | HIGH
EP-02 | APOD/SPOD | FREETOWN SPOD — Throughput Capacity Insufficient for MRO 2/3 Alone | One-brigade staging constraint, 12-hour working day, 2 berths: throughput ceiling reached quickly. Sequential force flow only. | CONAKRY TA MUST be signed. LCC/Div HQ to flow via CONAKRY. Purple gate formally agreed before D-Day. | LOW | HIGH | CRITICAL
EP-03 | APOD/SPOD | CONAKRY SPOD — Technical Agreement Unsigned | Essential for MRO 2/3. TA not signed. No lethal force on GUINEAn soil constraint complicates force protection. Pass/fail for MRO 2/3. | Immediate J5 action to secure TA. Maritime harbour protection quid pro quo. J4 cannot plan CONAKRY as confirmed until TA signed. | LOW | CRITICAL | CRITICAL
EP-06 | APOD/SPOD | IO/NGO Competition for Port Infrastructure | UNMSL/UNOCHA/UNJLC require same port access. MRO 3 explicitly flags this. Every IO/NGO ship displaces a military RoRo. | CIMIC-led deconfliction mechanism before D-Day. Dedicated traffic windows for military vs humanitarian cargo. | MEDIUM | HIGH | HIGH
F-01 | Class III | Fuel Demand Exceeds SPOD Capacity at MRO 2/3 | MRO 3 daily fuel demand alone exceeds FREETOWN SPOD mixed cargo capacity. MRO 2 at upper limit without CONAKRY. Arithmetic, not estimate. | Fuel as priority commodity. CONAKRY essential. GAMBIA for MRO 3. Fuel role-specialisation nation in CJSOR. | LOW | HIGH | CRITICAL
F-04 | Class III | No Fuel Role-Specialisation Nation Confirmed | Without a fuel lead nation, Class III defaults to parallel national procurement — generating artificial scarcity and incompatible systems. | Identify and propose fuel nation at force generation conference. Submit to COMJFC. Include in CJSOR. | LOW | HIGH | CRITICAL
MSR-01 | MSR Security | FREETOWN-Bo MSR Under Active Interdiction | Current AFRC/RUF attacks on UN convoys. Essential for Southern Province supply. Cannot be bypassed. | Route clearance and escort as a combat task preceding all logistics movement. Convoy Support Centres mandatory. | HIGH | HIGH | HIGH
MSR-04 | MSR Security | Rainy Season Onset — Feeder and Secondary Roads Impassable | May 2026 rainy season starts immediately. Feeder roads (0% paved) inaccessible. Secondary roads degrade. Only 925km primary paved roads usable. | All logistics plans based on primary roads only. Forces off primary roads MUST have pre-positioned 30+ DOS stocks. | MEDIUM | HIGH | HIGH
HNS-01 | HNS | GoSL Near-Collapse — HNS Unreliable | Port workers, local contracts, infrastructure access all dependent on functioning GoSL. Near-collapse assessed. Treating GoSL HNS as baseline = false planning foundation. | Every GoSL logistics function must have NATO organic or commercial alternative. OLRT confirms HNS status within 72 hours. | HIGH | HIGH | HIGH
HNS-02 | HNS | GUINEA HNS Politically Conditioned | No lethal force on GUINEAn soil. TA unsigned. Essential for MRO 2/3. Political conditions could change. | J5 diplomatic action. Maritime quid pro quo. Plan CONAKRY as confirmed ONLY after TA signed. | LOW | CRITICAL | CRITICAL
HNS-05 | HNS | Contracting/External Sustainment — No Enabling Budget Yet | Commercial contracts cannot begin without authority. Pre-execution contracting is the external sustainment baseline for all MROs. Serial 7 explicitly requires enabling budget. | Submit contracting plan and enabling budget request to COMJFC immediately. NAC/SACEUR authority required. | HIGH | HIGH | HIGH
RS-01 | RSOMI | JLSG Not Front-Loaded — Deployment Phase Failure Risk | If JLSG arrives with main force rather than 7 days before, every subsequent ship and aircraft waits. Time cannot be recovered. | JLSG in ACTPRED package as first lift. Non-negotiable sequencing requirement. | HIGH | HIGH | HIGH
RS-05 | RSOMI | RoRo Vessels Vulnerable to LIBERIAn Interdiction | LIBERIAn submarine and air capability. Merchant vessels = high-value targets. Deployment phase = maximum vulnerability window. | Naval escort from D-Day. SSK and SNMG tasked for RoRo escort as primary mission. | HIGH | HIGH | HIGH
CD-01 | Competing Demands | Civil-Military Resource Competition | WAFOR fuel/water demand crowds out civilian supply to hospitals and water pumping. Artificial scarcity generated without coordination. | Civil-military logistics coordination cell from D+0. Protected fuel/water aGLOCations for critical civilian infrastructure. | HIGH | HIGH | HIGH
GC-06 | Governance | LIBERIAn ISR on Logistics Infrastructure | LIBERIA has persistent ISR on LUNGI, FREETOWN SPOD, and LUNGI-FREETOWN crossing. Logistics build-up phase observed in real-time. Strike on RoRo or SPOD could be catastrophic. | Logistics base hardening and stock dispersal. Deception re: deployment sequence. Cyber protection of LUNGI Airport logistics systems. | HIGH | HIGH | HIGH
GC-07 | Governance | JLSN Not Yet Activated | Logistics nodes not yet linked. No node commanders designated. Without formal activation, nodes operate in isolation and cannot redirect cargo or resources. | Formal JLSN activation as J4 command task in pre-execution. JLSN architecture approved by COMJFC before D-Day. | HIGH | HIGH | HIGH

## Acronyms
Acronyms
Acronym | Explanation
4Ds | Distance, Destination, Demand, Duration — doctrinal JDP 4-00 logistics planning lens
ACTPRED | Activation / pre-deployment activity or request used here for early activation of enabling forces before main deployment.
AFRC | Armed Forces Revolutionary Council.
AJP | Allied Joint Publication.
ALP-16 | Allied Logistic Publication 16; referenced for munitions/explosives risk assessment.
APOD | Air Port of Debarkation.
ARF | Allied Reaction Force.
Avn Bn | Aviation Battalion.
Bde | Brigade.
BG | Battlegroup.
CD | Competing Demands — internal workbook factor category tag.
CDOS | Combat Days of Supply.
CIMIC | Civil-Military Cooperation.
CJEX | Combined Joint European Exercise.
CJSOR | Combined Joint Statement of Requirements.
CJTF | Combined Joint Task Force.
Cl | Class of supply, such as Cl I, Cl III, Cl V.
COA | Course of Action.
COMJFC | Commander Joint Force Command.
CONAKRY | CONAKRY, GUINEA; used as an alternate/essential SPOD/APOD location in the workbook.
CONOPS | Concept of Operations.
COPD | Comprehensive Operations Planning Directive.
COR | Critical Operational Requirement — workbook term for pass/fail or serious J4 requirements.
CR | Critical Requirement.
CRM | Crisis Response Measure.
CRSV | Conflict-Related Sexual Violence.
CSC | Convoy Support Centre.
CV | Critical Vulnerability.
DIRLAUTH | Direct Liaison Authorized.
DOS | Days of Supply.
EO | Electro-Optical.
EP | Entry Point — internal workbook factor category tag for APOD/SPOD nodes.
F | Fuel / Class III — internal workbook factor category tag.
FOC | Full Operating Capability.
FREETOWN | FREETOWN, SIERRA LEONE; primary SPOD/logistics base area in the workbook.
GAMBIA | GAMBIA; used as a possible contingency/third entry point in the workbook.
GC | Governance / Cross-Cutting — internal workbook factor category tag.
GoSL | Government of SIERRA LEONE.
GUINEA | Republic of GUINEA; host nation for CONAKRY SPOD/APOD in the workbook.
HI | Hierarchy of logistic considerations --- based on the scenario
HN | Host Nation.
HNS | Host Nation Support.
HQ | Headquarters.
ID | Identifier.
IDP | Internally Displaced Person.
IEC | Information / engagement context; not explicitly defined in workbook, use only if separately confirmed.
IO | International Organisation.
IOC | Initial Operating Capability.
ISR | Intelligence, Surveillance and Reconnaissance.
JDP | Joint Doctrine Publication.
JLSG | Joint Logistics Support Group.
JLSN | Joint Logistics Support Network.
JOA | Joint Operations Area.
JOPG | Joint Operations Planning Group.
LBU | Logistics Base Unit.
LCC | Land Component Command / Commander.
LEGAD | Legal Advisor.
LOC | Line of Communication.
LUNGI | Lungi International Airport; primary APOD in the workbook.
MAB | Mission Analysis Brief.
MANPAD | Man-Portable Air Defence system.
MANPADS | Man-Portable Air Defence Systems.
MEDEVAC | Medical Evacuation.
MRO | Military Response Option.
MSA | Mutual Support Agreement.
MSO | Military Strategic Objective.
MSR | Main Supply Route.
MT | Metric Tonnes.
MT/DOS | Metric Tonnes per Day of Supply.
MTF | Medical Treatment Facility.
NAC | North Atlantic Council.
NATO | North Atlantic Treaty Organization.
NGO | Non-Governmental Organisation.
NSE | National Support Element.
OLRT | Operational Liaison and Reconnaissance Team.
OPCOM | Operational Command.
OPLAN | Operation Plan.
POD | Port of Debarkation.
POL | Petroleum, Oils and Lubricants.
PSO | Peace Support Operation.
REFS | References.
ROE | Rules of Engagement.
RoRo | Roll-on/Roll-off shipping.
RS | RSOMI / deployment — internal workbook factor category tag.
RSOI | Reception, Staging, Onward Movement and Integration.
RSOM | Reception, Staging and Onward Movement.
RSOMI | Reception, Staging, Onward Movement and Integration.
RUF | Revolutionary United Front.
SA-14 | SA-14 Gremlin MANPADS
SACEUR | Supreme Allied Commander Europe.
SAR | Synthetic Aperture Radar.
SIGINT | Signals Intelligence.
SL | SIERRA LEONE.
SLFNA | FREETOWN port code used in the workbook.
SNMG | Standing NATO Maritime Group.
SOFA | Status of Forces Agreement.
SOI | Standing Operating Instruction / Standard Operating Instruction, depending on national usage.
SOP | Standard Operating Procedure.
SPOD | Sea Port of Debarkation.
SSK | Diesel-electric attack submarine.
TA | Technical Agreement.
TCN | Troop Contributing Nation.
TOO | Theatre of Operations.
UN | United Nations.
UNJLC | United Nations Joint Logistics Centre.
UNMSL | United Nations Mission in SIERRA LEONE, scenario-specific.
UNOCHA | United Nations Office for the Coordination of Humanitarian Affairs.
UNSCR | United Nations Security Council Resolution.
WAFOR | West African Force.